## Cover Sheet
DEPARTMENT OF
REGISTRAR-RECORDER/COUNTY CLERK
REQUEST FOR PROPOSALS —
J.1 IMPLEMENTATION REQUIREMENTS MATRIX RESPONSE TEMPLATE
FOR
ELECTION MANAGEMENT SYSTEM
IMPLEMENTATION AND SERVICES
RFP: #21-006
2021-08-16
---------------------------------------------------------------------------------
Prepared By
County of Los Angeles
Registrar-Recorder/County Clerk — Contracts Section Room 7211
12400 Imperial Highway Norwalk, CA 90650
www.lavote.net

## J.1 - Instructions
Department of Registrar-Recorder/County Clerk RFP
Election Management System Implementation and Services
RFP: #21-006
J.1 – Implementation Requirements Matrix
Name of Proposer: | <Insert Proposer Name Here>
Instructions
This Response Template contains the Implementation Requirements requested by the Los Angeles County Registrar-Recorder/County Clerk for the Election Management System (EMS). Instructions: The Proposer shall use the response codes below to indicate whether the proposed System meets the requirements. Complete this Response Template and submit as an MS Excel file as part of the Proposer's Technical Proposal.
Field | Instructions
Req. # | This should be used to refer to requirements in correspondence. DO NOT EDIT THIS FIELD.
Requirement | The detailed description of the requirement. DO NOT EDIT THIS FIELD.
Requirement Met | Proposer's response whether the technical requirement will be met by its solution. Yes: Requirement will be met. Modification: Proposed modification to requirement that will be met. Note: Modifications must be explained under 'Suggested Modification to Requirement or Clarifying Comments'. No: Requirement will not be met.
Suggested Modification to Requirement or Clarifying Comments | Provide comments/explanation on the Proposer's response, where required.

## Project Management
Department of Registrar-Recorder/County Clerk RFP
Election Management System Implementation and Services
RFP: #21-006
J.1 – Implementation Requirements Matrix |  | Name of Proposer: | <Insert Proposer Name Here>
PROJECT MANAGEMENT REQUIREMENTS
Req. # | Requirement | Requirement Met | Suggested Modification to Requirement or Clarifying Comments
IMP-1 | The Proposer shall develop each of the Project Initiation and Management Deliverables outlined in the Implementation Statement of Work in compliance with the Project Schedule and complete the Deliverables approval process as agreed to in the Contract.
IMP-2 | The Proposer shall support the County in its review of each of the Project Initiation and Management Deliverables outlined in the Implementation Statement of Work.
IMP-3 | The Proposer shall provide, employ, maintain, and execute a robust project management methodology that complies with the Project Management Institute (PMI) standards, or other similar industry best practices.
IMP-4 | The Proposer shall collaborate with the County to align all project management processes, templates, and standards with County standards where applicable or receive approvals for exceptions.
IMP-5 | The Proposer shall collaborate with the County Program Manager to ensure Deliverables are completed and approved in a timely fashion by the due dates established in the Project Schedule.
IMP-6 | The Proposer shall produce a Deliverables Expectation Document (DED) for each Deliverable and submit for review by the County's Program Manager prior to commencing work on any Deliverable.
IMP-7 | The Proposer shall perform all project management processes outlined in the Project Management Plan throughout the duration of the Project.
IMP-8 | The Proposer shall provide all project management documents (e.g., Project Management Plan, Project Schedule, etc.) using Microsoft software products and/or PDF. The software version to be used must follow the County's approved standards.
IMP-9 | The Proposer shall leverage the County's standards and templates for Deliverables, where applicable, or receive approval from the County to use Proposer's own templates.
IMP-10 | The Proposer shall provide bi-weekly Project Status Reports, monthly Elections Steering Committee Status Reports, and any additional status reports outlined in the Statement of Work or as requested by the County.
IMP-11 | The Proposer shall lead all weekly project status meetings.
IMP-12 | The Proposer shall provide an agenda no less than one (1) day prior to project status meetings.
IMP-13 | The Proposer shall identify, track, and manage Project risks, issues, action items, and decision management processes and logs in compliance with the approach outlined in the Project Management Plan.
IMP-14 | The Proposer shall collaborate with the County staff to mitigate risks, resolve issues, complete action items, and drive decisions.
IMP-15 | The Proposer shall track progress against the baseline Project Schedule and report any deviations to the County. At the County's discretion, the Proposer shall develop recovery plans to address major deviations.
IMP-16 | The Proposer shall, in the event of a transition between its staff, provide reason for personnel change, identify personnel who meet or exceed qualifications of the personnel being replaced, and receive County approval before formally transitioning staff.
IMP-17 | The Proposer shall provide an Engagement Director who will serve as the primary point of contact with the County for the duration of the Contract. The Engagement Director must be empowered to act on behalf of the Proposer. The Engagement Director must resolve any problems and contract disputes in an efficient and timely manner related to items such as roles, responsibilities, performance against Service Level Agreements (SLAs), and/or Change Requests.
IMP-18 | The Proposer shall provide a minimum of one full-time Project Manager, who holds a current Project Management Professional (PMP) certification from the Project Management Institute (PMI) or equivalent and is certified in Agile methodologies.
IMP-19 | The Proposer shall actively maintain Project documentation for the duration of the Project on the approved Project Information Library.
IMP-20 | The Proposer shall perform the tasks required to close out the Project including updating all appropriate documentation, migrating the documentation to the County's control, and providing support during the transition.

## Requirements Validation
Department of Registrar-Recorder/County Clerk RFP
Election Management System Implementation and Services
RFP: #21-006
J.1 – Implementation Requirements Matrix |  | Name of Proposer: | <Insert Proposer Name Here>
REQUIREMENTS VALIDATION REQUIREMENTS
Req. # | Requirement | Requirement Met | Suggested Modification to Requirement or Clarifying Comments
IMP-21 | The Proposer shall develop each of the Requirements Validation Deliverables outlined in the Implementation Statement of Work in compliance with the Project Schedule and complete the Deliverables approval process as agreed to in the Contract.
IMP-22 | The Proposer shall support the County in its review of each of the Requirements Validation Deliverables outlined in the Implementation Statement of Work.
IMP-23 | The Proposer shall develop a plan to conduct interviews and group workshops to refine the Use Cases, Functional Requirements, and Non-Functional Requirements.
IMP-24 | The Proposer shall support the County in identifying all the staff with the required business knowledge who should attend the Use Case validation workshops.
IMP-25 | The Proposer shall support the County in identifying all the staff with the required business knowledge who should attend the Requirements validation workshops.
IMP-26 | The Proposer shall document a detailed gap analysis to identify any custom development required (beyond configuration).
IMP-27 | The Proposer shall finalize the System interface requirements for signoff by the County.
IMP-28 | The Proposer shall review and finalize Use Cases and Requirement Traceability Matrices and obtain written approval from the County before development or implementation.
IMP-29 | The Proposer shall ensure that Requirements are traced throughout the Project lifecycle and produce finalized Requirements Traceability Matrices, which map the requirements to specific test cases. This must include removing and adding requirements as the scope changes through Change Requests.
IMP-30 | The Proposer shall facilitate working sessions with County subject matter experts to inform the Product Backlog.
IMP-31 | The Proposer shall develop the Product Backlog, including defining the Epics and developing the respective User Stories.
IMP-32 | The Proposer shall facilitate backlog grooming sessions with the County to prioritize and refine the User Stories.
IMP-33 | The Proposer shall use an agile project management tool for the Project.

## Design, Dev, Config
Department of Registrar-Recorder/County Clerk RFP
Election Management System Implementation and Services
RFP: #21-006
J.1 – Implementation Requirements Matrix |  | Name of Proposer: | <Insert Proposer Name Here>
DESIGN, DEVELOPMENT AND CONFIGURATION REQUIREMENTS
Req. # | Requirement | Requirement Met | Suggested Modification to Requirement or Clarifying Comments
IMP-34 | The Proposer shall develop each of the Design Deliverables outlined in the Implementation Statement of Work in compliance with the Project Schedule and complete the Deliverables approval process as agreed to in the Contract.
IMP-35 | The Proposer shall support the County in its review of each of the Design Deliverables outlined in the Implementation Statement of Work.
IMP-36 | The Proposer shall develop each of the Development and Configuration Deliverables outlined in the Implementation Statement of Work in compliance with the Project Schedule and complete the Deliverables approval process as agreed to in the Contract.
IMP-37 | The Proposer shall support the County in its review of each of the Development and Configuration Deliverables outlined in the Implementation Statement of Work.
IMP-38 | The Proposer shall define the Solution Architecture that meets the County's requirements and can be technically realized.
IMP-39 | The Proposer shall provide tools to manage the version control on software configurations and custom development.
IMP-40 | The Proposer shall agree that all code developed to augment functionality, that is not part of the core product, shall be incorporated into the product and be supported in similar fashion as the core product.
IMP-41 | The Proposer shall develop the Security Plan, detailing how security will be controlled during Implementation.
IMP-42 | The Proposer shall develop an access control matrix, which defines the access profiles and identifies the roles and permissions each user will receive.
IMP-43 | The Proposer shall monitor ongoing security threat changes and respond to evolving threats.

## Integration
Department of Registrar-Recorder/County Clerk RFP
Election Management System Implementation and Services
RFP: #21-006
J.1 – Implementation Requirements Matrix |  | Name of Proposer: | <Insert Proposer Name Here>
INTEGRATION REQUIREMENTS
Req. # | Requirement | Requirement Met | Suggested Modification to Requirement or Clarifying Comments
IMP-44 | The Proposer shall develop each of the Integration Deliverables outlined in the Implementation Statement of Work in compliance with the Project Schedule and complete the Deliverables approval process as agreed to in the Contract.
IMP-45 | The Proposer shall support the County in its review of each of the Integration Deliverables outlined in the Implementation Statement of Work.
IMP-46 | The Proposer shall complete the application to initiate the EMS certification process with the California Secretary of State.
IMP-47 | The Proposer shall be responsible for successful certification between the EMS and VoteCal prior to Go-Live. Note: The County expects to use the System by the 2024 Presidential Primaries.
IMP-48 | The Proposer shall assign a VoteCal Certification Lead who is responsible for leading the effort to achieve VoteCal certification from the California Secretary of State.
IMP-49 | The Proposer shall prepare a VoteCal Certification Plan, track progress against the Plan, and provide weekly updates to the County.
IMP-50 | The Proposer shall establish the EMS and VoteCal integration.
IMP-51 | The Proposer shall document all interface specifications.
IMP-52 | The Proposer shall develop all interfaces to/from the proposed System.
IMP-53 | The Proposer shall facilitate sessions in support of interface development to external and internal data sources.
IMP-54 | The Proposer shall develop a detailed plan for each interface with support from the external system vendor resources. These will include, at a minimum, the technical approach, tasks required (including development and testing timing and approach), design documentation, data format and support approach.
IMP-55 | The Proposer shall perform all necessary design, configuration, development, and testing activities required to implement the interfaces.

## Data Migration
Department of Registrar-Recorder/County Clerk RFP
Election Management System Implementation and Services
RFP: #21-006
J.1 – Implementation Requirements Matrix |  | Name of Proposer: | <Insert Proposer Name Here>
DATA MIGRATION REQUIREMENTS
Req. # | Requirement | Requirement Met | Suggested Modification to Requirement or Clarifying Comments
IMP-56 | The Proposer shall develop each of the Data Migration Deliverables outlined in the Implementation Statement of Work in compliance with the Project Schedule and complete the Deliverables approval process as agreed to in the Contract.
IMP-57 | The Proposer shall support the County in its review of each of the Data Migration Deliverables outlined in the Implementation Statement of Work.
IMP-58 | The Proposer shall provide a Data Migration Plan that includes elements such as methodology and best practice model that optimizes the data migration cycle time.
IMP-59 | The Proposer shall migrate data from the identified source system(s), ensuring no duplicate records in alignment with the County's and State's data standards.
IMP-60 | The Proposer shall develop procedures to migrate data from legacy systems, in alignment with the Data Migration Plan.
IMP-61 | The Proposer shall develop scripts to automatically migrate high volume data objects, in alignment with the Data Migration Plan.
IMP-62 | The Proposer shall lead data migration activities including developing a schedule for all data mapping and migration activities and identifying resource requirements (e.g., Proposer, County, external system vendors, etc.).
IMP-63 | The Proposer shall perform data conversion, mapping and loading, and soliciting County input as required.
IMP-64 | The Proposer shall perform data testing and validation and provide tools to the County to confirm the data testing results.
IMP-65 | The Proposer shall support the County's review of data migration testing results.
IMP-66 | The Proposer shall perform and pass, at a minimum, one trial data migration prior to User Acceptance Testing (UAT) using a full or partial dataset as determined by the County during planning phase.
IMP-67 | The Proposer shall acquire authorization from the County for the use of production system resources (legacy data or source files), or data derived from the the County's production resources.
IMP-68 | The Proposer shall coordinate all automated and manual data loads during data migration testing and UAT.
IMP-69 | The Proposer shall provide a data dictionary, data models, data flow models, process models and other related planning and design documents to the County.
IMP-70 | The Proposer shall ensure data dictionary, data models, data flow models, process models and other related planning and design documents are in alignment with the County's standards.
IMP-71 | The Proposer shall be an active member on the County's data governance body and adhere to the established data governance standards.
IMP-72 | The Proposer shall provide tools to minimize manual effort required to migration data from legacy systems.
IMP-73 | The Proposer shall provide tools to streamline the data migration effort by identifying common error conditions (e.g., duplicate records) and minimizing manual effort during the data migration process by automating where possible the corrective action process (e.g., merging duplicate records). Redudant records shall be maintained for future reference.
IMP-74 | The Proposer shall partner with the County in data mapping workshops to ensure integrity of the existing data model after migration.
IMP-75 | The Proposer shall provide an environment for the unique purpose of running the data migration process in order to obtain County's approval of the migrated data.
IMP-76 | The Proposer shall enable the County's technical staff to extract data using a tool that allows for rule based extraction of data for the purposes of validating the data conversion.
IMP-77 | The Proposer shall provide the County with an electronic report of data that did not migrate into the Proposer's application.
IMP-78 | The Proposer shall provide data migration tools, scripts, language, templates, queries, reports, conflict resolution, error handling, and root cause analysis processes.
IMP-79 | The Proposer shall implement a process to identify gaps in the data including how to prevent the data gap through automated processes and appropriate algorithms to prevent human intervention.
IMP-80 | The Proposer shall implement a methodology and identify techniques to ensure no data is left behind and all the data has been migrated to the final destination and/or to an environment that requires further analysis due to exception handling and control total processes.
IMP-81 | The Proposer shall identify the potential and average number of data conversions (test conversions) required to ensure end-to-end data integrity and reliability.
IMP-82 | The Proposer shall identify any potential additional hardware, software, tools, or training required to be purchased to ensure smooth data migration.
IMP-83 | The Proposer shall identify the resource skill set needed (i.e., background, accountability, authority, and responsibility) for data migration.
IMP-84 | The Proposer shall provide a report to identify load times for dataset conversion and migration.
IMP-85 | The Proposer shall provide a data comparison report comparing source to target for selected objects.
IMP-86 | The Proposer shall provide a difference report between source migration data and target environment.

## Testing
Department of Registrar-Recorder/County Clerk RFP
Election Management System Implementation and Services
RFP: #21-006
J.1 – Implementation Requirements Matrix |  | Name of Proposer: | <Insert Proposer Name Here>
TESTING REQUIREMENTS
Req. # | Requirement | Requirement Met | Suggested Modification to Requirement or Clarifying Comments
IMP-87 | The Proposer shall develop each of the Testing Deliverables outlined in the Implementation Statement of Work in compliance with the Project Schedule and complete the Deliverables approval process as agreed to in the Contract.
IMP-88 | The Proposer shall support the County in its review of each of the Testing Deliverables outlined in the Implementation Statement of Work.
IMP-89 | The Proposer shall plan and orchestrate all testing activities, including User Acceptance Testing (UAT). However, execution of UAT test cases will be conducted by the County.
IMP-90 | The Proposer shall perform all necessary testing, with the exception of User Acceptance Testing, that is required to implement the System.
IMP-91 | The Proposer shall provide a proven testing methodology.
IMP-92 | The Proposer shall develop a comprehensive Test Plan reflecting each testing cycle including entrance and exit criteria, approach to defect management, and progress tracking.
IMP-93 | The Proposer shall provide and develop Test Scripts, with the County's input.
IMP-94 | The Proposer shall provide and develop Test Scenarios, with the County's input.
IMP-95 | The Proposer shall lead testing activities and ensure that results are properly documented and approved by the County.
IMP-96 | The Proposer shall participate in checkpoint meetings, including testing phase entrance and exit gates, and provide relevant information for the County to make informed decisions to migrate into/out of specific testing phases.
IMP-97 | The Proposer shall ensure the schedule accommodates for the provision of the required test data for each testing cycle and produce a de-identified test data set.
IMP-98 | The Proposer shall refine the test documents, procedures, and scripts throughout development and through full System acceptance to reflect the as-built design and current requirements.
IMP-99 | The Proposer shall run validation and testing software against externally facing Internet applications to help identify potential security issues. The Proposer shall repair any deficiencies found during this testing.
IMP-100 | The Proposer shall test time-sensitive elements. As System events contain date and time-sensitive elements, the testing infrastructure must provide a method of altering and synchronizing the System date throughout each test phase. This requires the ability to change the System date and time in some scenarios.
IMP-101 | The Proposer shall provide and leverage a testing tool/test harness which supports automated regression testing and other testing functions.
IMP-102 | The Proposer shall ensure that the System undergoes proper performance and load testing based on the County's standards and data volume.
IMP-103 | The Proposer shall support the County during acceptance testing.

## Reporting
Department of Registrar-Recorder/County Clerk RFP
Election Management System Implementation and Services
RFP: #21-006
J.1 – Implementation Requirements Matrix |  | Name of Proposer: | <Insert Proposer Name Here>
REPORTING REQUIREMENTS
Req. # | Requirement | Requirement Met | Suggested Modification to Requirement or Clarifying Comments
IMP-104 | The Proposer shall develop each of the Reporting Deliverables outlined in the Implementation Statement of Work in compliance with the Project Schedule and complete the Deliverables approval process as agreed to in the Contract.
IMP-105 | The Proposer shall support the County in its review of each of the Reporting Deliverables outlined in the Implementation Statement of Work.
IMP-106 | The Proposer shall identify opportunities to consolidate reports into ad-hoc, parameter driven reports.
IMP-107 | The System shall be capable of providing: - Predefined operational reports - Self-service ad-hoc reports - Self-service reporting and analytics - Dashboards
IMP-108 | The Proposer shall ensure the System captures the data required to produce County required reports.
IMP-109 | The Proposer shall facilitate working sessions with the County to define the list of reports.
IMP-110 | The Proposer shall document specifications for each report identified by the County.
IMP-111 | The Proposer shall design, build, and test all reports identified by the County.

## OCM, Training & KT
Department of Registrar-Recorder/County Clerk RFP
Election Management System Implementation and Services
RFP: #21-006
J.1 – Implementation Requirements Matrix |  | Name of Proposer: | <Insert Proposer Name Here>
ORGANIZATIONAL CHANGE MANAGEMENT, TRAINING AND KNOWLEDGE TRANSFER REQUIREMENTS
Req. # | Requirement | Requirement Met | Suggested Modification to Requirement or Clarifying Comments
IMP-112 | The Proposer shall develop each of the Organizational Change Management Deliverables outlined in the Implementation Statement of Work in compliance with the Project Schedule and complete the Deliverables approval process as agreed to in the Contract.
IMP-113 | The Proposer shall support the County in its review and refinement of each of the Organizational Change Management Deliverables outlined in the Implementation Statement of Work.
IMP-114 | The Proposer shall collaborate with the County to recommend the approach, guidance, and mentorship to support the County through the successful transition to new operational and technical processes enabled by the System.
IMP-115 | The Proposer shall periodically assess the County's readiness, willingness, and ability to adopt business process and system changes.
IMP-116 | The Proposer shall provide recommendations to improve the County's readiness based on findings from each Change Readiness Assessment.
IMP-117 | The Proposer shall propose and define, in collaboration with the County, the Organizational Change Management and Communications Strategy.
IMP-118 | The Proposer shall capture the Organizational Change Management and Communications Plan to execute the Organization Change Management and Communications Strategy. It shall reflect information gathered from the Change Readiness Assessment.
IMP-119 | The Proposer shall collaborate with the County to conduct Organizational Change Management activities throughout the Project and provide an Organizational Change Management framework including communications targeted at specific stakeholders (e.g. type of end-user, supervisors, executives), surveys, etc.
IMP-120 | The Proposer shall develop commmunication materials, with input from the County.
IMP-121 | The Proposer shall develop each of the Training and Knowledge Transfer Deliverables outlined in the Implementation Statement of Work in compliance with the Project Schedule and complete the Deliverables approval process as agreed to in the Contract.
IMP-122 | The Proposer shall support the County in its review of each of the Training and Knowledge Transfer Deliverables outlined in the Implementation Statement of Work.
IMP-123 | The Proposer shall propose and define, in collaboration with the County, the Training and Knowledge Transfer Strategy.
IMP-124 | The Proposer shall define the Training and Knowledge Transfer Plan to execute the Training and Knowledge Transfer Strategy. It shall reflect information gathered from the Change Readiness Assessment.
IMP-125 | The Proposer shall provide a software tool that supports generation, presentation, and maintenance of computer-based trainings.
IMP-126 | The Proposer shall provide, manage, and support training environments.
IMP-127 | The Proposer shall provide trainers to conduct the requisite training in compliance with the Project Schedule.
IMP-128 | The Proposer shall provide and manage/support appropriate testing environments that will be leveraged for training purposes.
IMP-129 | The Proposer shall produce all required training and knowledge transfer materials to address identified training needs. This will include, but may not be limited to, instructor-led classroom training, computer-based trainings, train-the-trainer, training manuals and interactive trainings.
IMP-130 | The Proposer shall produce all help files including interactive online help files targeted at System users.
IMP-131 | The Proposer shall schedule all training during regular work hours as approved by the County, unless advance approval is received from the County for specific training at other times.
IMP-132 | The Proposer shall schedule staff training in a manner that is least disruptive to normal election operations.
IMP-133 | The Proposer shall track County attendance at training sessions.
IMP-134 | The Proposer shall document evidence of each trainee's competence to use the System to conduct their duties.
IMP-135 | The Proposer shall produce a training dataset to be deployed to the training environment along with deployment instructions to the County staff.
IMP-136 | The Proposer shall identify the level of knowledge transfer required between the Project team and the Maintenance and Support team to support, maintain and operate the System as well as the skill sets necessary, with the County's agreement.
IMP-137 | The Proposer shall perform Knowledge Transfer activities throughout the Project and measure progress.
IMP-138 | The Proposer shall coordinate with the County throughout the Project to ensure that the County is available in a timely manner for knowledge transfer activities.
IMP-139 | The Proposer shall provide training to the technical/operations team on any System changes and changes in System components functionality/architecture for the duration of the Project.
IMP-140 | The Proposer shall include a full user manual that describes all system functions.

## Implementation and Go-Live
Department of Registrar-Recorder/County Clerk RFP
Election Management System Implementation and Services
RFP: #21-006
J.1 – Implementation Requirements Matrix |  | Name of Proposer: | <Insert Proposer Name Here>
ROLL-OUT AND GO-LIVE REQUIREMENTS
Req. # | Requirement | Requirement Met | Suggested Modification to Requirement or Clarifying Comments
IMP-141 | The Proposer shall develop each of the Implementation Deliverables outlined in the Implementation Statement of Work in compliance with the Project Schedule and complete the Deliverables approval process as agreed to in the Contract.
IMP-142 | The Proposer shall support the County in its review of each of the Implementation Deliverables outlined in the Implementation Statement of Work.
IMP-143 | The Proposer shall implement the System for the County's use by the 2024 Presidential Primaries.
IMP-144 | The Proposer shall assess the pre-implementation readiness of each part of the organization and document the status in a pre-implementation readiness assessment.
IMP-145 | The Proposer shall facilitate check-point meetings, with County input, to assess health of the roll-out and decide if changes are required.
IMP-146 | The Proposer shall lead the deployment preparation activities, including workshops and documentation.
IMP-147 | The Proposer shall provide and maintain a Deployment Plan, including an hourly go-live schedule and plan, with associated responsibilities for each task.
IMP-148 | The Proposer shall lead a production readiness assessment.
IMP-149 | The Proposer shall provide a deployment staffing and support model.
IMP-150 | The Proposer shall lead the System deployment activities, including any activities required by the County for successful deployment of the System.
IMP-151 | The Proposer shall support the County's governance body in making decisions regarding defect and issue resolution during deployment.
IMP-152 | The Proposer shall develop the Disaster Recovery/Business Continuity Plan.
IMP-153 | The System shall provide on-site supoprt with personnel who are technically competent to fully support the System, including VoteCal integration and data synchronization, to resolve issues during deployment.
IMP-154 | The Proposer shall provide a plan for post-deployment assessments.
IMP-155 | The Proposer shall facilitate lessons learned sessions and document findings.